## Sheet1
Date | Name | Task
07-07-2023 | Venkata Sandeep Reddy Sabbella | Movie Theater Management - This business provides information about movies that are playing currently and upcoming in a theater.It also gives information about upcoming movies that are avaliable in the theater. It shows the timing and screens for the movies based on dates.
| Pavan Kumar Reddy Vuyyuru | Movie Theater Management - This business provides information about movies that are playing currently and upcoming in a theater.It also gives information about upcoming movies that are avaliable in the theater. It shows the timing and screens for the movies based on dates.
| Rithvik Varma Thotakura | Movie Theater Management - This business provides information about movies that are playing currently and upcoming in a theater.It also gives information about upcoming movies that are avaliable in the theater. It shows the timing and screens for the movies based on dates.
| Samrat Rajesh Jyoti | Movie Theater Management - This business provides information about movies that are playing currently and upcoming in a theater.It also gives information about upcoming movies that are avaliable in the theater. It shows the timing and screens for the movies based on dates.
10-07-2023 | Venkata Sandeep Reddy Sabbella | commonly all together researched on how web page want to be designed purpose, number of pages and guidelines.
| Pavan Kumar Reddy Vuyyuru | commonly all together researched on how web page want to be designed purpose, number of pages and guidelines.
| Rithvik Varma Thotakura | commonly all together researched on how web page want to be designed purpose, number of pages and guidelines.
| Samrat Rajesh Jyoti | commonly all together researched on how web page want to be designed purpose, number of pages and guidelines.
11-07-2023 | Venkata Sandeep Reddy Sabbella | searched for pages content and started creating project pages.
| Pavan Kumar Reddy Vuyyuru | Research on how header look a like and gathered images that are required in header.
| Rithvik Varma Thotakura | research on pages content from another websites and seen samples.
| Samrat Rajesh Jyoti | researched on about us page content and gathered some info.
12-07-2023 | Venkata Sandeep Reddy Sabbella | Gathered images for my pages (now_palying and contact us).
| Pavan Kumar Reddy Vuyyuru | Researched for page colors,fonts and wireframe structure of project.
| Rithvik Varma Thotakura | created footer and images for my page.
| Samrat Rajesh Jyoti | started working on about_us.html page and styling.
13-07-2023 | Venkata Sandeep Reddy Sabbella | created navbar and home page(30%).
| Pavan Kumar Reddy Vuyyuru | created header and started creating pages(show_timings - 75% done)
| Rithvik Varma Thotakura | changed footer and working on page upcoming movies
| Samrat Rajesh Jyoti | working on about_us page.
2023-07-15 | Venkata Sandeep Reddy Sabbella | completed 90% of the home page
| Pavan Kumar Reddy Vuyyuru | 100% completed the show-timings
| Rithvik Varma Thotakura | working on upcoming movies page(50% completed)
| Samrat Rajesh Jyoti | completed 80% of about us page
2023-07-17 | Venkata Sandeep Reddy Sabbella | completed homepage and started working on the contact us page(40% completed)
| Pavan Kumar Reddy Vuyyuru | complted 80% of the trailers page
| Rithvik Varma Thotakura | complted 70% of upcoming movies page and started working on terms and conditions page
| Samrat Rajesh Jyoti | completed desktop view for about us and started working on media queries for mobile view
2023-07-24 | Venkata Sandeep Reddy Sabbella | completed contact us page and added map, form to collect feedbackand table to display hours of operation
| Pavan Kumar Reddy Vuyyuru | completed 100% of the trailer page
| Rithvik Varma Thotakura | upcoming movies page has been completed 100%
| Samrat Rajesh Jyoti | completed 100% of about us page
2023-07-25 | Venkata Sandeep Reddy Sabbella | completed all three (desktop,tab,mobile) wireframes for contact us page
| Pavan Kumar Reddy Vuyyuru | adjusted responsiveness for home page and contact us page
| Rithvik Varma Thotakura | terms and conditions page is finished 100%
| Samrat Rajesh Jyoti | drawn wireframe for desktop view for about us page
2023-07-26 | Venkata Sandeep Reddy Sabbella | completed all three (desktop,tab,mobile) wireframes for home page
| Pavan Kumar Reddy Vuyyuru | adjusted responsiveness for trailers page and showtimings page
| Rithvik Varma Thotakura | drawn the wireframe for desktop view for upcoming movies
| Samrat Rajesh Jyoti | drawn the wireframe for tab for about us page
2023-07-28 | Venkata Sandeep Reddy Sabbella | Completed all desigining works like coding and etc
| Pavan Kumar Reddy Vuyyuru | Completed all desigining works like coding and etc
| Rithvik Varma Thotakura | Completed all desigining works like coding and etc
| Samrat Rajesh Jyoti | Completed all desigining works like coding and etc
2023-07-31 | Venkata Sandeep Reddy Sabbella | Completed the documentation,wireframes and sitemap works
| Pavan Kumar Reddy Vuyyuru | Completed the documentation,wireframes and sitemap works
| Rithvik Varma Thotakura | Completed the documentation,wireframes and sitemap works
| Samrat Rajesh Jyoti | Completed the documentation,wireframes and sitemap works